## Description
RACI Code | Description
R | Responsible: The person who is ultimately responsible for delivering the task successfully (applies to one role only).
A | Accountable: The person who has ultimate accountability and authority; they are the person to whom “R” is accountable (usually applies to one role only) .
C | Consulted: Someone whose input adds value and/or buy-in is essential for ultimate implementation (multiple roles allowed).
I | Informed: The person or groups of individuals who need to be notified of results or actions taken but don’t need to be involved in the decision-making process (multiple roles allowed).
Sheet | Description
Simple | The "Simple" RACI is suitable for an immature delivery team or a non-technical reader who isn't a member of the delivery team.
Detailed | The "Detailed" RACI is a complete version for a delivery team entering maturity.
Role | Description
Operations Manager | Consumer of services provided by RPA capability - responsible for managing alignment with business strategy Accountable for RPA business case
Operations SME | Subject Mater Exepert from Operations Team
IT | Responsible for managing inward and outward dependencies with IT. Gatekeeper for demand on RPA capability from IT
Head of RPA | The Head of RPA role is one of the most important roles in RPA being the face and voice of robotic process automation within the organisation. The person in this role will be expected to operate at and with all levels and departments within an organisation to optimise the efficiency and benefits for robotic process automation.
Technical Architect | Technical Architects have responsibility for providing solutions that integrate all technical aspects of the Blue Prism infrastructure with existing architectures, including networks, virtual environments and security frameworks.
Delivery Manager /Team | Implements RPA Projects in alignment with the Delivery Methodology and Framework
Design Authority | The Design Authority (DA) is responsible for maintaining the development integrity of the Blue Prism solution and its constituent processes and objects.
Process Analyst | The Process Analyst role captures the detailed key stroke level mapping instructions of what the human workers perform when completing the process. This level of detail is required for processes identified for automation.
Solution Designer | The Blue Prism Solution Designer is responsible for designing efficient, resilient, scalable, secure and reusable unattended Blue Prism solutions that adhere to Blue Prism solution design best practices.
Lead Developer | Senior Process Developers have responsibility for supporting the creation and evolution of the delivery framework, mentoring other process developers and delivering automated processes.
Developer | Process Developers have responsibility for developing and delivering automated processes plus mentoring non-certified developers.
Tester | Test Analysts have responsibility for identifying test conditions, creating test cases and assisting on test execution and validation of test results.
Release Manager | The Blue Prism Release Manager shall provide control of the flow of deployments and releases across multiple environments or across multiple teams eliminating the potential risks of a release deployment.
Process Controller | The Process Controller will schedule and run Blue Prism processes, ensure the stability of the Blue Prism IT environment, investigate any issues in the live processes, and raise change requests or support calls where required.
Support Analyst | Support Analysts have responsibility for providing first line support for the Blue Prism production processes.

## Simple List
Delivery Activities | Operations Manager | Operations SME | IT | Head of RPA | Design Authority | Process Analyst | Lead Developer | Developer | Tester | Process Controller
Define
· Define AS IS Process
· Process demonstration | A | R |  | I |  | R
· SME interview | I | C |  | A |  | R
· Definition document creation | C | R |  | A |  | R
· Definition document walkthrough | C | C |  | A |  | R
· Business case review | A/R | I | I | A/R |  | I
· Estimate benefits
· Business need analysis | A | C |  | A |  | R
· Cost-benefit analysis | A | C |  | A |  | R
· Discover TO BE functional requirements
· Requirements interview | I | C |  | A |  | R | I | C
Design
· Design TO BE process based on AS IS definition and functional requirements
· Design document creation | I | I | C | A | C | C | C | R
· Design document walkthrough | I | I | C | A | C | C | C | R
· Agree automation scope
· Scope document walkthrough | C | I | C | A | C | C | R | C
· Agree test approach for TO BE process
· Discover availability of live data in pre-production environments | I | C | C | A |  | R |  | C | C
· Assess risk of using live data in pre-production | C: A/R; A: A/R
· Assess effort require to prepare test data | I | C |  | A |  | C |  | C | R
· Discuss implementation options and controlled go-live | A/R | C | C | A/R |  |  | C |  | C | I
· Agree on the responsibility of the operation for TO BE process
· Solution design walkthrough | C | I | I | A | I | C | R |  |  | C
· Service model walkthrough | C | I | I | A | I | C | R |  |  | C
· Exception handling walkthrough | C | I | I | A | I | C | R |  |  | C
Build
· Build TO BE process
· Solution development |  | C |  | A | C |  | C | R
· QA review
· QA review for Objects and Processes | bar: A; R
Test
· Test TO BE process
· Unit Testing | I: C; A: A; R: C; C: R
· System Integration Testing | [8 empty] | R | bar: I; A; R
· UAT | A | R |  | A |  |  | C | C | C
Run
· Run BAU
· Monitor BAU | A | C | I | A |  |  | C |  |  | R
· MI
· Generate MI | C: A; C: I; A: I; C: C |  | R
· Calculate benefits
· Data analysis | C: A/R; A: A/R

## Detailed List
Delivery Activities | Operations Manager | Operations SME | IT | Head of RPA | Technical Architect | Delivery Manager /Team | Design Authority | Process Analyst | Solution Designer | Lead Developer | Developer | Tester | Release Manager | Process Controller | Support Analyst
Conceive
· Select automation candidates
· Business case creation | A | R |  | A |  |  |  | R
· Triage, assess, analyse automation candidates | A | R | C | A |  |  | C | R
· Approve automation candidates | A/R | C | I | A/R |  | C | C | C
· Determine the priority order in scheduling | A/R | I | C | A/R |  | C | C | C
· Discover TO BE functional requirements
· SME interview | I | C |  | I |  | A |  | R
· Requirements interview | C | C |  | I |  | A |  | R
Define
· Estimate benefits
· Business need analysis | A | C |  | A |  | I |  | R
· Cost-benefit analysis | A | C |  | A |  | I |  | R
· Define AS IS process
· Process demonstration | A | R |  | I |  | A |  | C
· Definition document creation | I | A |  | I |  | A |  | R
· Business case review | A/R | C |  | A/R |  | I | C | C
Validate Definition
· Agree AS IS process definition | I | C |  |  |  | A | C | R |  | C
· Definition document walkthrough | I | C |  |  |  | A | C | R |  | C
Approve Definition
· Approve AS IS process definition | A | R |  |  |  | I |  | C |  | I
· Definition document walkthrough | A | R |  |  |  | I |  | C |  | I
· Agree TO BE function requirements
· Requirements review | C | C | C |  |  | A |  | R |  | C
Design
· Document TO BE process design based on AS IS definition and functional requirements
· Solution Design document creation | C | C | C |  | C | A | C | C | R | C
Validate Design
· Solution Design document walkthrough |  | C |  |  | C | A | C | C | R | C
· Validate TO BE process design |  | C | C |  | C | A | C | C | R
· Scope document walkthrough |  | C |  |  | C | A | C | C | R | C
· Agree automation scope | A | R |  | A |  |  | C |  | R
Approve Design
· Approve TO BE process design | A/R | C | C | A/R | C | C | C |  | C
· Approve automation scope | A/R | C | C | A/R | C | C | C |  | C
· Create Test approach for TO BE process
· Discover availability of live data in pre-production environments |  | C | C |  |  | A |  | R |  |  | C | C
· Assess risk of using live data in pre-production | A | R |  |  |  | A |  | R
· Assess effort required to prepare test data | A | C |  |  |  | A |  | C |  |  | C | R
· Discuss implementation options and controlled go-live | A/R | C | C |  |  | A/R |  |  |  | C |  | C | C |  | C
· Validate Test approach for TO BE process
· Review live data in pre-production environments | A | R | C |  |  | A |  | R | C | C |  | C
· Review risk of using live data in pre-production | A | R | C |  |  | A |  | R | C | C |  | C
· Review effort require to prepare test data |  | C | C |  |  | A |  | C |  |  |  | R
· Review implementation options and controlled go-live | C | I | C | C |  | R/A | C | R |  | C | R | C | C | C
· Agree test approach for TO BE process
· Agree on live data in pre-production environments | A/R | C | C | A/R |  | A |  | C | C | C |  | C
· Agree on Risk of using live data in pre-production | A/R | C | C | A/R |  | A |  | C | C | C |  | C
· Agree on Effort require to prepare test data | A | R | C |  |  | A |  | C |  |  |  | R
· Agree on Implementation options and controlled go-live | A/R | C | C | C | C | A/R | C | R |  | C |  | C | C
· Validate the responsibility of the operation for TO BE process
· Operational impact document creation | C | C |  |  |  | A |  | R |  | C |  |  |  | C
· Operational impact document walkthrough | A | C |  |  | I | C |  | R |  | C |  |  |  | C
· Agree on the responsibility of the operation for TO BE process
· Solution design walkthrough | I | C |  |  |  | A | C |  | R |  |  |  |  | C
· Service model walkthrough | I | C |  |  |  | A | C |  | R |  |  |  |  | C
· Exception handling walkthrough | I | C |  |  |  | A | C |  | R |  |  |  |  | C
· Agree on the responsibility of the operation for TO BE process | A/R | C |  | A/R |  | C | C |  | C |  |  |  |  | I | I
· Plan delivery
· Define and sequence activities | C |  |  | A |  | R | C |  | C | C |  |  | C
· Estimate effort and resource and time for activities | C |  |  | A | C | R |  |  |  | C |  |  | C
· Develop delivery plan | C | I | I | A | I | R | I | I |  | I | I | I | I | I | I
· Agree Delivery plan
· Review and approve delivery plan | R | I | C | A |  | R |  |  |  | C |  | C | C | C
Instruct Build
· Build Instruction for Objects and Processes
· Design, review and agree on designs for objects and processes | [8 empty] | C | A | R | bar: R to I
Build
· Build TO BE process
· Solution development | [8 empty] | C | A | R | bar: R to I
· QA review
· QA review for Objects and Processes | [8 empty] | C | R | bar: R to I
Test
· Test solution
· Unit testing | [9 empty] | C | R | bar: R
· Configuration testing | [9 empty] | C | R | bar: R
· Validation testing | [9 empty] | C | C | R | bar: I; R
· Verification testing | [9 empty] | C | C | R | bar: I; R
Accept
· Solution accepted
· UAT | C | R | I | I |  | A |  |  |  | C | C | R
Approve Deployment
· Deployment agreed
· Develop deployment activities | A: I; R: A; I: C |  |  | R |  | C
· Review deployment criteria | I: C; A: I; R: A; I: C |  |  |  |  | R
· Plan deployment |  | C | C | I |  | R | I |  |  |  | C |  | C
Package
· Package a solution
· Create a solution package | [9 empty] | C | R |  | C | bar: R
Validate Package
· Validate solution package
· Review and modify a solution package | [9 empty] | R | C |  | R | bar: R
Initial Deployment
· Initial go-live
· Deploy, verify and validate deployment | [9 empty] | C | C |  | R | C | I | bar: C to A; R
Hyper Care
· Monitor initial results
· Verify and validate case results | A | R | I | I |  | I |  |  |  | C | C
· Measure performance
· Monitor, control and measure performance | A | R | I | I |  | I | [7 empty] | R | R
· Agree full deployment
· Review performance results | C: A; I: R; A: A; R: I | [6 empty] | R
· Update Implementation Plan | C | I | C | I |  | R | [6 empty] | C
· Agree on full deployment | A/R | I | C | A/R | C | R | [6 empty] | R | I | I
Full Deployment
· Deploy solution
· Export, Import and Verify a release | I | I | I | I | I | A | I | I | I | C | R | I | R | I | I
BAU Run
· Run BAU
· Monitor BAU | I: A; I: R; I: I; I: I; A: A; R: I; I: R; I: C
· Create MI
· Report MI | I: A; I: I; I: I; A: A; R: I; I: C; I: R
· Calculate benefits
· Data analysis | I: A; I: R; I: I; I: I; I: I; A: I; I: I
BAU Maintain
· Monitor performance
· Monitor performance, exception rate, workload and logging | I: A; I: R; I: C; I: I; I: I; A: A; I: R; I: C
Retire
· Decommission automation
· Plan decommission | I: C; I: C; I: A; A: R; R: C; I: C
· Review and agree on decommission | I: A/R; I: I; I: A/R; I: A/R; I: C; R: I; I: I