## Development Test Plans Overview
TEST PLAN OVERVIEW
Configuration Testing | Scenario Testing
Context | Context
The testing here will be a mixture of both formal and informal testing; some of it will consist of routine automated system tests and others will be more process specific. The goal is to ensure that the process is in a fit state to begin Verification with a Subject Matter Expert (SME). | The verification phase forms part of configuration, and therefore the automated solution will still be incomplete. The purpose of configuration is twofold: firstly it allows new screens to be configured which can only be reached using live data (eg the "Account Closed" screen can only be seen after closing an account); secondly, it allows a large variety of business scenarios to be tested so that confidence can be established in the solution ahead of Acceptance Testing.
Since scenarios are being verified (and in some cases configured) for the very first time, the solution is not considered "ready" – the verification phase is the means by which the solution will arrive at this state.
Environment | Environment
All testing will take place in the Blue Prism Configuration Environment. Any target system processing will be initially performed in a test system where applicable. Currently a test Customer Gateway system is available. It is essential that the test target system is a precise mirror of the production system. | Verification takes place in the configuration environment, because an agile and rapid improvement cycle will take place – the verification phase is indeed part of the configuration phase.
Testing Scope | Testing Scope
The verification phase focuses mainly on confirming interface functionality within the process – ensuring that objects and components have been correctly created or modified, and are correctly used from within the process, as per design. | The verification phase focuses mainly on Business Scenario Verification – configuring the process to correctly deal with each business scenario, as per the design.
It may also include limited instances of Controlled Failure Tests – verifying the behaviour of the solution in certain situations such as environment failure. Eg what if one of the target applications is unavailable? | It may also include limited instances of Controlled Failure Tests – verifying the behaviour of the solution in certain situations such as environment failure. Eg What if an input source does not match the expected file format?
Test Requirements | Test Requirements
For configuration testing, the configuration environment and cases used for development can be used. There are no additional environmental requirements. | Various resources will need to be organised, such as:
· Sources of both real life and imaginary data representing the defined scenarios
· Subject Matter Experts (SMEs) to help conduct testing and verify outputs
· Sufficient volumes of real-world data to satisfy the Live-Data Testing requirements.
Progression Criteria | Progression Criteria
There are not usually any strict progression criteria; instead the Blue Prism Configuration Analyst must be satisfied that s/he is ready to proceed into the Verification Phase with the SME, and that the time spent together will be productive. A project manager will often wish to discuss the nature of the testing conducted so far with the Blue Prism Configuration Analyst, and s/he should be prepared for this. | An informal set of criteria will be required to define the end of the Verification Phase. Typically, this will be a minimum set of scenarios and volumes to be worked.

## Reference Training
Reference Training
The following guidelines will help complete training for this delivery documentation.
Title | Description
Lifecycle Orientation | This is a Blue Prism portal page, providing a brief explanation of the Blue Prism Lifecycle Orientation and related documents. Blue Prism portal path: Home> Learning> Lifecycle Orientation
Delivery Roadmap | This document describes the end-to-end steps in creating and delivering a Blue Prism process solution. The key process phases are outlined from Initial Process Assessment through to Testing. Blue Prism portal path: Home> Documents
Lifecycle Orientation Sample Delivery Documents | All prescribed delivery documents are fully completed. These are referenced within the Delivery Roadmap and provide an example of the content and level of detail required. Blue Prism portal path: Home> Documents
Process Delivery Methodology | The Blue Prism Process Delivery Methodology is a proven means of delivering ongoing business benefit through process automation using a controlled and structured Automation Framework. Blue Prism portal path: Home> Documents
Test Phases Overview | This Test Phases document describes the standard test phases during a Blue Prism project to ensure that automated solutions are delivered into live with the optimum possible level of testing throughout development to ensure that processes are delivered that meet business requirements and contain the minimum possible levels of system exceptions. Blue Prism portal path: Home> Documents
Testing Approach | This document is a guidelines of the testing approaches that should be considered when testing RPA solutions. Blue Prism portal path: Home> Documents
Blue Prism - Introducing Your Process to Live Data | This guide outlines the methods available on how to introduce your process to live data. It should be considered prior to defining your delivery methodology and test approach. Blue Prism portal path: Home> Documents

## Testing Plan Timeline
TEST PLAN TIMELINE
| Process Name: | [6 empty] | Project Manager:
Developer:
SME:
Testing Cycle | Scenario Coverage
Verification Cycle 1 | Work 1 cases and sample 100% to ensure all actions are correct. |  |  |  |  | UAT test scenarios will aim to have a confidence level of 80% however this may not be possible under certain live data conditions If we cannot achieve 80% under live data UAT testing then the Business will have to decide to accept the risks or continue testing
Verification Cycle 2 | Work 4 cases and sample 100% to ensure all actions are correct.
Verification Cycle 3 | Work 10 cases and sample 100% to ensure all actions are correct.
UAT Cycle 4 | Work 20 cases and sample 100% to ensure all actions are correct.
UAT Cycle 5 | Work 50 cases and sample 70% to ensure all actions are correct.
UAT Cycle 6 | Work 100 cases and sample 30% to ensure all actions are correct.
Key | Testing Stages
| Configuration Testing | Verification Cycle 1 | Verification Cycle 2 | Verification Cycle 3 | UAT Cycle 4 | UAT Cycle 5 | UAT Cycle 6 | Prod Dress Rehearsal | UAT Complete | End to End Testing / Perf Test | Go / No Go Decision | Go Live Day | Warranty
Not Started
In Progress
Completed
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy | BANK HOLIDAY UK
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
dd/mm/yyyy
CURRENT
POSITION

## Configuration Test Plan
CONFIGURATION TEST PLAN
|  |  | Number of Configuration Tests | 2
| Process Name: |  | Passed Configuration Tests | 0%
ID # | Name | Description | Notes | Pass?
1 | Start System A | The process can start and log into <System A> and <System B> using Credentials. | If the <System B> password expires the process will generate a new password and update the credentials. | No
2 | Etc – please continue
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Process Testing Scenarios
SCENARIO TEST PLANNING
| Process Name: |  |  |  |  | Count | %
[5 empty] | High Level Scenarios | 2
[5 empty] | Verified/Passed | 0 | 0%
[5 empty] | N/A (out of scope) | 0 | 0%
[5 empty] | Remaining / Not Tested | 0 | 0%
[5 empty] | Cases Worked | 1
ID # | Name | Description | Expected Outcome | Cases Worked | Notes | In / Out of Scope | Pass?
1 | System Start and Log in | The opening of an account using … etc. | The account should be successfully opened, including X,Y,Z as verified using A,B,C. | 1 | To include one male one female and one child. | In Scope | Not Covered
2 | Etc – please continue
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Faults Identified BP
FAULTS IDENTIFIED
|  | Process Name: |  |  | Status |  | Priority
[5 empty] | Open | 0 | High | 0
[5 empty] | Open - Investigating | 0 | Medium | 0
[5 empty] | Closed - fixed | 0 | Low | 0
[5 empty] | Closed - opened in error | 0 | "Nice to have" | 0
[5 empty] | Awaiting Retest | 0 | Not Prioritised | 0
[5 empty] | On Hold | 0
[5 empty] | TOTAL | 0 |  | 0
ID | Date | Process | Fault Description | Comments / Actions Taken |  | Priority | Status | Date Resolved
D001
D002
D003
D004
D005
D006
D007
D008
D009
D010
D011
D012
D013
D014
D015
D016
D017
D018
D019
D020
D021
D022
D023
D024
D025
D026
D027
D028
D029
D030
D031
D032
D033
D034
D035
D036
D037
D038
D039
D040
D041
D042
D043
D044
D045
D046
D047
D048
D049
D050